## INSTRUCTIONS
Notes
1 | This Risk Register is a template, and contents can be added, deleted, or modified to suit specific project risks.
2 | The Risk Register shall be used with appropriate guidance documents.
3 | The Owner is responsible for modifying the includded risks, identifying the Impacts, Owner, and response. Those identified in this register may be used, or modified for any project. As these are generic, owner's will likely have to add to this list for project specific risks.
4 | Page size is best suited to 11" x 17" print
5 | Assign a risk Identification Number (ID) that corresponsed with work breakdown structure for the project. If no WBS being utilized, assign sequential numbers.
6 | Update or modify any text to suit your project

## Risk Register
Owner |  |  |  | Date | [11 empty] | Revision #
Project Title |  |  |  | Project Number | [11 empty] | Completed by
Risk Identification |  |  |  | Impacts to Project | [11 empty] | Risk Rating |  |  |  |  | Risk Owner |  |  |  | Response |  | Monitoring
ID | Phase | Risk Category | Description | Increased Cost | Schedule / Project Delay | Poor Quality | Health and Safety | Performance Issues | Compliance | Legal /Disputes | Reputation or Stakeholder support | Project Cancellation | Budget Shortfall or Reallocation | Design Errors or Omissions | Scope Creep | Impact | Probability | Impact | Probability | Risk Score | Owner | Contractor | Sub- Contractor | Consultant | Response Approach | Response Plan | Status | Risk Closed Date
| Initiation | Application Quality | The UR fails to include sufficient excavation costs in the estimate, during construction existing interfering infrastructure is discovered, or does not include allowable contingencies and escalation |  | X |  |  | X |  |  | X | [6 empty] | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Include all work for the project in the estimate - Engage a consultant to evaluate the problem and scope a suitable solution - Utilize current estimating practices and data - Detail the project scope based on field data, not google earth
| Initiation | Application Quality | UR fails to include accurate KML file showing the location and extent of work | X | X |  |  |  | X | X |  | X | X | X | X |  |  | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Include KML file that accurately shows the work of the project - Ensure all stakeholders are aware of the extent and scope of project
| Initiation | Application Quality | UR fails to include Risk Management documentation with application |  | X | [6 empty] | X | X |  | X |  |  | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - UR to ensure a comprehensive risk analysis is completed and submitted with application
| All Phases | Communication | Unauthorized access data/files can result in sensitive information being misused or disclosed | [6 empty] | X | X | [6 empty] | #N/A | #N/A | #N/A | X | X |  | X | Mitigate | - All parties to have back- ups of data - Develop and follow IT policies - Ensure personnel are trained in data security
| All Phases | Communication | Delays in responding to questions |  | X | X | [7 empty] | X |  |  |  | #N/A | #N/A | #N/A | X | X | X | X | Mitigate | - Project requirements should identify expectations for communications including timelines and responsibilities
| All Phases | Communication | Communication gaps, or lack of communication | X | X | X | X | X | X | X | X |  |  |  | X |  |  | #N/A | #N/A | #N/A | X | X | X | X | Mitigate | - Owner to identify and communicate chains of communication - Host regular meetings - Define commination Matrix
| All Phases | Communication | Ambiguous language / missing content in tendered documents | X | X | X |  | X |  | X | [7 empty] | #N/A | #N/A | #N/A | X |  |  | X | Mitigate | - Implement rigorous review process - Use simple and concise language - Issue clarifying documents as during Tender and construction phases
| All Phases | Communication | Lack of communication | X | X | X | X | X | X | X | X | X | X | X | X |  |  | #N/A | #N/A | #N/A | X | X | X | X | Mitigate | - Owner to identify and communicate chains of communication - Host Regular Meetings - Document decisions - Develop communication matrix
| All Phases | Community and Stakeholder Engagement | Media coverage of the project may be unfavorable | [6 empty] | X | X | [6 empty] | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Communicate potential impacts to those impacted by the project
| All Phases | Community and Stakeholder Engagement | Operation and Maintenance costs may result in increased taxes or fees | [6 empty] | X | X | [6 empty] | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Organize public information sessions - Engage the council - Create a plan for external stakeholder involvement
| All Phases | Community and Stakeholder Engagement | Local residents may oppose the project due to impact on their living standard, increased taxes, or other reasons | [6 empty] | X | X | [6 empty] | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Provide early communication, with emphasis on positive outcomes
| All Phases | Community and Stakeholder Engagement | Lack of transparency or engagement with local communities, resulting in opposition | [6 empty] | X | X | [6 empty] | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Regularly update stakeholders - Hold public meetings - Provide transparent information - Address concerns promptly
| All Phases | Consultant / Contractor | Consultant fails to meet deadlines | X | X | [5 empty] | X | X | X |  |  |  |  | #N/A | #N/A | #N/A | X |  |  | X | Mitigate | - Carefully select consultants, contractors and subcontractors - Define clear contracts with performance metrics - Establish regular oversight of their work - Establish a process for quickly resolving disputes - Establish experience and qualification standards
| All Phases | Consultant / Contractor | Contractor fails to meet deadlines | X | X | [5 empty] | X | X | X |  |  |  |  | #N/A | #N/A | #N/A | X |  |  | X | Mitigate | - Carefully select consultants, contractors and subcontractors - Define clear contracts with performance metrics - Establish regular oversight of their work - Establish a process for quickly resolving disputes - Establish experience and qualification standards
|  | Cultural Heritage and Social Identity | Construction disrupting historically significant sites or the cultural traditions of local communities |  | X |  |  |  |  | X | X | [6 empty] | #N/A | #N/A | #N/A |  |  |  |  | Mitigate | - Conduct cultural and heritage impact assessments - Engage with cultural leaders and local communities - Modify the project design to avoid cultural conflicts
| Initiation | Environmental | Environmental contamination of potential sites or adjacent properties | X | X |  | X | [10 empty] | #N/A | #N/A | #N/A | X | X | X | X | Mitigate | - Conduct environmental assessments early into the design process to minimize impact to design / construction
| Initiation | Environmental | Failure to address Climate Change in the design |  |  |  | X | X |  | X | X | [6 empty] | #N/A | #N/A | #N/A | X |  |  | X | Mitigate | - Conduct climate lens assessment early in the project - Ensure current codes, standards, regulations are utilized in the design and construction - Ensure robust design features - Incorporate sustainable and environmentally friendly materials and process
| Construction | Environmental | Extreme weather events resulting in an inability to complete construction work | X | X |  | X | [10 empty] | #N/A | #N/A | #N/A | X | X | X | X | Mitigate | - Tender and start construction at times of seasonal advantage - Contractor to build weather delays into the project construction timeline - Include terms in the contract to address potential of such events - use resilient construction practices
| Construction | Environmental | Poor environmental control during construction resulting environmentally impacted conditions as a result of the project | X |  |  | X | X |  | X | [7 empty] | #N/A | #N/A | #N/A | X | X | X | X | Mitigate | - Contractor to use proper waste management procedures and green construction practices - Include clauses in contract documents to put the responsibility on the contractor - Require maintenance records and regular inspections of operating equipment - Require immediate notification of spills, or environmental damage
|  | Environmental | Failure to complete Environmental or Hazardous Material Assessments | X | X | X | X | [7 empty] | X |  |  | #N/A | #N/A | #N/A | X |  |  | X | Mitigate | - Evaluate need for assessments prior to start of work - have assessments completed by competent professionals
| Design | Financial | Escalation in operational costs may lead to differing opinions on project approach | X | [13 empty] | #N/A | #N/A | #N/A | X |  |  | X | Mitigate | - Owner to outline expectations to factor into design - Consultant to complete full project cost analysis including operation, maintenance and replacement
| All Phases | Financial | Failure for Owner to drive the project in a timely manner such that estimates are outdated by the time the construction starts | X | [13 empty] | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Assess the expected capital requirements for construction during the early concept phase - Identify concerns early in design so that measures can be taken to adjust design, request scope changes, etc. - Prioritize critical items / consider deferring non- critical items
| All Phases | Financial | Escalation in labour costs | X | [13 empty] | #N/A | #N/A | #N/A | X | X |  | X | Mitigate | - Utilize fixed price / unit price contracts
| Construction | Financial | Material and equipment costs may increase over time | X | [13 empty] | #N/A | #N/A | #N/A | X | X | X | X | Mitigate | - Work will be fixed price, unit price
| Initiation | Financial | Failure to secure enough financing |  | X | X |  |  |  |  | X | X | X |  |  |  |  | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Accurate cost estimation - Secure sufficient financing before starting - Create a detailed budget - Establish a contingency fund
| All Phases | Financial | Budget overruns |  | X | X |  |  |  |  | X | X | [5 empty] | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Accurate cost estimation - Monitor spending closely
| Construction | Health and Safety | Personnel / equipment getting in the way of operations during construction |  | X |  | X | X | [9 empty] | #N/A | #N/A | #N/A |  | X |  |  | Transfer | - Require site specific safety plan from Consultant and Contractors - Require site training and signage
| Construction | Health and Safety | Misunderstanding of safety responsibilities may lead to a misunderstanding of safety requirements and expectations, increasing the chances of safety- related incidents |  |  |  | X |  | X | X | [7 empty] | #N/A | #N/A | #N/A | X | X | X | X | Transfer | - Contractor and Consultant to develop a site- specific safety plan including emergency plans, contact lists, ensure personnel are trained, ensure use of PPE, ensure subcontractors are certified and insured -Ensure clarification of safety responsibilities in included in contracts - Considering hiring a safety professional for the project - Utilize COR certified contractors only
| Construction | Health and Safety | Major injury or death on the construction site |  | X |  | X |  |  |  |  | X | [5 empty] | #N/A | #N/A | #N/A | X | X | X | X | Transfer | - Contractor and Consultant to develop a site- specific safety plan including emergency plans, contact lists, ensure personnel are trained, ensure use of PPE, ensure subcontractors are certified and insured -Ensure clarification of safety responsibilities in included in contracts - Considering hiring a safety professional for the project
| Construction | Health and Safety | The public may be curious about the project and may attempt to enter the site while construction is ongoing |  |  |  | X |  |  | X | [7 empty] | #N/A | #N/A | #N/A |  |  |  | X | Transfer | - Contractor to ensure safety and security on site utilizing fencing/hording s necessary - Use of sign- in system, adequate signage - Enable security if necessary
| Construction | Health and Safety | Use of Hazardous materials on site |  |  |  | X | [10 empty] | #N/A | #N/A | #N/A | X | X |  |  | Transfer | - Ensure contractor has all proper PPE and precautions in place
| Initiation | Inadequate Documentation and Reporting | Ambiguous or incomplete technical requirements | X |  | X |  | X |  |  | X |  |  |  | X |  |  | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Define project requirements clearly - Seek clarifications and design reviews
| All Phases | Inadequate Documentation and Reporting | Missing or incomplete reports | [6 empty] | X |  |  |  | X | X |  |  | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Detailed review of submissions prior to acceptance. - Request modifications as needed
| All Phases | Inadequate Documentation and Reporting | Failure to track budget expenditures and encumbrances | X | [8 empty] | X |  |  |  |  | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Implement stringent budget tracking process
| All Phases | Inadequate Documentation and Reporting | Insufficient record-keeping | X | X | X | X | X | X | X | X | X | X | X | X |  |  | #N/A | #N/A | #N/A | X | X |  | X | Mitigate | - Ensure that all project activities, decisions, and changes are properly documented, including contracts, financial records, change orders, and meeting minutes - Keep an audit trail of key decisions and actions taken throughout the project to maintain transparency and accountability - Implement a regular reporting system to update stakeholders on project progress, budget status, and key risks.
| All Phases | Indigenous People and Lands | Lack of engagement with Indigenous groups, failure to recognize their rights, or conflicts over land use and resource allocation |  | X |  |  |  |  | X |  | X | [5 empty] | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Consultation and Engagement - Land use agreement reviews - Impact Assessments - Involve Indigenous leaders and knowledge holders in project planning and review - Workers complete Cultural Sensitivity Training - Formal agreements with Indigenous communities - Utilize sustainable practices to reduce harm to local ecosystems and traditional lands
| Initiation | Land Acquisition | Owner has not purchased the land from a private owner prior to starting the project | X | X | [9 empty] | X |  |  | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Ensure land is owned by the project Owner, or a land use agreement is in place prior to starting project
| All Phases | Legal and Regulatory | Poorly written contracts may generate confusion and changes | X | X | X |  | X | X | X | [7 empty] | #N/A | #N/A | #N/A | X |  |  | X | Mitigate | - Owner to develop a clear Statement of Requirements with help from the Owner's Engineer - Utilize standard contracts - Engage legal review
| All Phases | Legal and Regulatory | Permitting requirements (DFO, Transport Canada, ENVC) may be onerous |  | X | [12 empty] | #N/A | #N/A | #N/A |  | X |  | X | Mitigate | - Consultant to include pre-consultation for permit application and approval into the project schedule
| Design | Legal and Regulatory | Building code changes may result in significant changes to the design | X |  |  |  |  | X | [8 empty] | #N/A | #N/A | #N/A | X |  |  | X | Mitigate | - The project requirements will articulate code compliance - Designer to stay updated on potential changes, design to latest Building Code, consult with experts as required
| All Phases | Legal and Regulatory | Failure to secure necessary permits, complete necessary environmental assessments, non-compliance with zoning laws, or changes in regulations | X | X |  |  |  |  | X | [7 empty] | #N/A | #N/A | #N/A | X | X |  | X | Mitigate | - Ensure that all regulatory requirements are identified and adhered to early - Engage legal experts - Obtain all necessary permits before beginning construction - Compliance monitoring - Early engagement with Authorities
| All Phases | Political | Change in local or national government, leading to a shift in project priorities or funding cuts |  | X |  |  |  | X |  |  | X | [5 empty] | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Monitor political developments - Engage with political stakeholders early - Maintain flexible project plans that can accommodate changes in political direction
| All Phases | Political | Changes in policy, regulations | X | X |  |  |  | X | X | [7 empty] | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Engage consultant fluent in policy and regulations of governing bodies
|  | Project Management | Poor planning, lack of coordination, mismanagement of resources, scope creep, and/or inadequate documentation and reporting | X | X | X | X |  |  |  | X | X | X | X | X |  |  | #N/A | #N/A | #N/A | X | X |  | X | Mitigate | - Implement effective project management tools - Develop a clear project plan - Assign roles and responsibilities - Continuously monitor project progress - Realistic scheduling, including buffer time - Change Management Process - Develop and implement detailed quality assurance plans that include monitoring, inspections, and testing at key project milestones - Regular Inspections and Audits - Comprehensive Documentation - Experienced Project Managers
| Design | Quality Assurance / Control | Existing infrastructure condition unknown, causing issue with new infrastructure compatibility | X |  |  |  | X | [9 empty] | #N/A | #N/A | #N/A | X |  |  | X | Mitigate | - Understand needs and limitations of existing infrastructure
| Construction | Quality Assurance / Control | Poor quality construction | X | X | X | X |  |  |  | X | [6 empty] | #N/A | #N/A | #N/A |  | X |  | X | Transfer | - Contractor to manage and oversee subcontractors - Project requirements to include mandatory designer inspection
| Construction | Quality Assurance / Control | Use of substandard materials | X | X | X | X | X | [9 empty] | #N/A | #N/A | #N/A |  | X |  |  | Mitigate | - Shop drawing review process - Substitution of material approval process - On site monitoring and supervision
| Construction | Quality Assurance / Control | Insufficient Supervision | X | X | X | X | X | X | [8 empty] | #N/A | #N/A | #N/A |  | X |  |  | Mitigate | - Implement and monitor Quality Control processes -Monitoring program
| Design | Quality Assurance / Control | Design flaws | X | X | X | X | X |  |  | X |  |  | X |  |  |  | #N/A | #N/A | #N/A |  |  |  | X | Mitigate | - Specification and Drawing peer review - Implement and monitor Quality Control processes
X | Closeout | Reputation and Public Perception | Increased operational costs tend to increase consumer costs which may lead to public upset | [6 empty] | X | X | [6 empty] | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Owner to communicate impacts of operating cost on users, as well as the communicating benefits of major water quality improvements
| Construction | Reputation and Public Perception | Services used by both domestic and commercial uses must be maintained during construction |  | X | [5 empty] | X | [6 empty] | #N/A | #N/A | #N/A |  | X |  |  | Mitigate | - Ensure work is design / sequenced in a way that prevents disruptions - Require contractor to maintain and provide service
| Construction | Reputation and Public Perception | Extended working hours may be required to avoid traffic impacts and/or impacts to surrounding residents or businesses |  | X | [5 empty] | X | [6 empty] | #N/A | #N/A | #N/A |  | X |  |  | Mitigate | - Contractor to manage and understand local laws/approvals - Include restriction in contract documents
| Construction | Reputation and Public Perception | Disruptions / impacts to traffic and services in the construction area may result in public upset |  | X |  |  |  |  | X | X | [6 empty] | #N/A | #N/A | #N/A |  | X |  |  | Transfer | - Contractor to conduct traffic modelling, develop public notices, coordinate with Owner early, detours if necessary, consider flexible work hours, use quiet equipment where possible - Include restrictions in contract documents
| Construction | Reputation and Public Perception | Noise / proximity to nearby residents / businesses | [6 empty] | X | X | [6 empty] | #N/A | #N/A | #N/A |  | X |  |  | Transfer | - Contractor to develop plan to mitigate noise impacts, access to adjacent businesses, and free use of neighboring municipal infrastructure - Include restrictions in contract documents
| Construction | Reputation and Public Perception | Transportation of materials and equipment within a residential community | [6 empty] | X | X | [6 empty] | #N/A | #N/A | #N/A |  | X |  |  | Transfer | Contractor to conduct traffic impact assessments and pre- plan routes Attempt to transport during non- peak hours Use traffic control if necessary
| All Phases | Resource Management | Changes in project team members can result in lack of clarity as project is handed over to new members | X | X | X | [11 empty] | #N/A | #N/A | #N/A | X | X |  | X | Mitigate | - All parties to ensure decisions and goals are well- documented for future key personnel - Utilize project team member change process
| All Phases | Resource Management | The community is considered a rural part of the province, it may be more difficult to hire qualified personnel | X | [13 empty] | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Owner to make project attractive to Contractors through project definition - During construction, oversight of quality is critical
| Construction | Resource Management | Inadequate response due to lack of industry capacity, qualified bidders | X | [13 empty] | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Project should be well defined with appropriate risk allocation to avoid limiting bidder interest
| Construction | Resource Management | Contractor bankruptcy may result in work stopping, remobilization, and new personnel to educate on the project | X | X |  |  |  |  | X | X | [6 empty] | #N/A | #N/A | #N/A | X | X |  |  | Transfer | - Bonding requirements act as security against bankruptcy This does not include re- design work that may be required
| Construction | Resource Management | Equipment delivery may have long lead times |  | X | [12 empty] | #N/A | #N/A | #N/A |  | X |  |  | Mitigate | - Contractor to identify long lead items early - Initiate early procurement and pre- orders - Fix delivery schedules with suppliers and explore alternative vendors
| Construction | Resource Management | There is a limited number of accommodations for construction workers as the work area is remote | X | X | [12 empty] | #N/A | #N/A | #N/A | X | X |  |  | Mitigate | - The Contractor should assess requirements early, get group pricing from local hotels/rental properties - Hire local subcontractors that do not require accommodations
| Construction | Resource Management | Inadequate laydown area available for construction, it may increase the complexity of completing the project |  |  |  |  | X |  |  | X | [6 empty] | #N/A | #N/A | #N/A |  | X |  |  | Mitigate | - Contractor to consider construction requirements during design
| Construction | Resource Management | Difficulty coordinating performance testing and commissioning | X | X |  |  | X | [9 empty] | #N/A | #N/A | #N/A |  | X |  | X | Mitigate | - Contractor to develop a detailed timeline, list of requirements, engage commissioning vendors early
| Construction | Resource Management | Building materials being unavailable may result in a need to procure materials from other companies at a higher price / from further away | X | X | [12 empty] | #N/A | #N/A | #N/A |  | X |  |  | Mitigate | - Contractor to secure building materials early and have back- up suppliers available if necessary - Contract documents speaks to overages due to this - Unit Price contract
| All Phases | Schedule | Not meeting funding agreement timelines |  | X | [6 empty] | X | X |  |  |  |  | #N/A | #N/A | #N/A | X | X |  | X | Mitigate | - Develop plan that manages schedule to avoid issues - Ensure contracts are awarded on time - Include clauses in contract documents that Contractor is responsible for schedule after award - Include clauses in Consultant contract addressing responsibility to schedule
| All Phases | Schedule | The schedule does not have detail required to manage project appropriately |  | X | [6 empty] | X | [5 empty] | #N/A | #N/A | #N/A |  |  |  | X | Mitigate | - Ensure that all aspects of the project, including design, procurement, construction, and testing, are thoroughly planned - Include Critical Path items - Monitor progress - Adjust throughout
| All Phases | Schedule | There may be long lead times for utilities like NL Hydro | X | X | [12 empty] | #N/A | #N/A | #N/A |  | X |  |  | Mitigate | - Contractor to apply for permits and coordinate Utility work early in the project
| All Phases | Schedule | Weather Delays | X | X | [12 empty] | #N/A | #N/A | #N/A |  |  |  |  | Mitigate | - Allow time in the schedule to address potential weather issues given the seasons of construction.
| Design | Scope Creep | A lack of understanding of the project definition / purpose / end goal leads | X | X | X |  | X | [6 empty] | X |  |  | #N/A | #N/A | #N/A |  |  |  | X | Mitigate | - Develop a clear Statement of Requirements - Clearly define the project scope at the start including specific deliverables, timelines, and budgets
| Design | Scope Creep | Adding additional features to the project | X | X | [9 empty] | X |  |  | #N/A | #N/A | #N/A | X |  |  | X | Mitigate | - Develop project documents as complete as possible with existing records - Implement a Scope Change evaluation process
| Design | Scope Creep | Conflicts may arise from the coordination of multiple project phases | [11 empty] | X |  |  | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Develop project documents as complete as possible with existing records - Implement a Scope Change evaluation process
| Design | Scope Creep | A lack of required data for design, unknown conditions |  |  | X |  | X | [9 empty] | #N/A | #N/A | #N/A | X |  |  | X | Mitigate | - Complete a gap analysis to ensure sufficient data for detailed design or seek clarification
| Design | Scope Creep | A lack of understanding of the current operations / facilities | X | X | X | X | X | [9 empty] | #N/A | #N/A | #N/A |  |  |  | X | Mitigate | - Discuss operations needs with current operations staff - Review prior reports and basis of design for the project
| Design | Scope Creep | Operations staff may have expectations and/or opinions about how the system should be designed in order to optimize operations work | X | X |  |  | X |  |  | X |  |  |  | X |  |  | #N/A | #N/A | #N/A | X |  |  | X | Mitigate | - Engage operational staff at an early stage in the design process and address operational requirements
| Construction | Scope Creep | Damage to existing infrastructure may result in extra work to repair damages, involvement of other parties to fix damages, inability to use existing infrastructure while damaged, and/or water quality issues |  |  |  |  | X | [6 empty] | X |  |  | #N/A | #N/A | #N/A |  | X |  |  | Mitigate | - Conduct pre- construction survey - Employ non-invasive methods of construction - Follow safety plans - Employ experienced contractors - Sequence construction work so that subconsultants have space needed for work - Conduct regular inspections - Ensure construction personnel are trained
| Construction | Scope Creep | Unknown site conditions may lead to discovering existing issues to infrastructure during construction or discovering an inability to conduct work as per design | X | X | X |  | X | [5 empty] | X | X |  |  | #N/A | #N/A | #N/A | X |  |  | X | Mitigate | - Review historical data - Develop a contingency budget - Conduct inspections - Ensure routine maintenance is conducted
| Design | Scope Creep | Change orders may result in disagreements between parties | X | X |  |  |  |  | X | X | [6 empty] | #N/A | #N/A | #N/A | X | X |  | X | Mitigate | - The project requirements should identify areas of limited knowledge around existing conditions - Implement a change management process define scope as best as possible
| Construction | Security | If equipment or tools are damaged or stolen they would need to be replaced |  | X | [12 empty] | #N/A | #N/A | #N/A |  | X |  |  | Transfer | - Contractor to implement various access control measures to the site including secure storage, security, inventory items/check- in/check- out, inspections
| All Phases | Social | Displacement of residents | X | X | [5 empty] | X | X |  |  | X |  |  | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Relocation assistance and support services - Ensure that affected individuals are provided with adequate compensation
| All Phases | Social | Protests |  | X |  |  |  |  | X | X | [6 empty] | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Engage and communicate with the community, including cultural leaders early
| All Phases | Social | Social inequity | [6 empty] | X | X | [6 empty] | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Ensure the project addresses the needs of all social groups, particularly marginalized communities, by integrating social equity into the design and decision-making process
| All Phases | Social | Exclusion individuals or groups in the community | [6 empty] | X | X | [6 empty] | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Ensure that public infrastructure, such as transit or healthcare, is accessible to all residents, including vulnerable groups
| All Phases | Social | Cultural heritage impacts, social identity loss | [6 empty] | X | X | [6 empty] | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Conduct thorough cultural and heritage assessments to understand and address potential impacts on local traditions, sacred sites, and historical landmarks
| All Phases | Social | Opposition to the project | [6 empty] | X | X | [6 empty] | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Engage and communicate with the community, including cultural leaders early
|  | Supply Chain | Delays in the delivery of construction materials or equipment due to logistical issues or global supply chain disruptions | X | X | X | [11 empty] | #N/A | #N/A | #N/A |  | X |  |  | Mitigate | - Secure multiple suppliers - Maintain buffer stock of critical materials - Establish contingency plans for supply chain disruptions
| Construction | Technology and Innovation | The existing infrastructure must be able to be integrated with new while maintaining service |  |  |  |  | X |  | X | X | [6 empty] | #N/A | #N/A | #N/A |  | X |  | X | Mitigate | - Ensure compatibility throughout design process - Conduct testing prior to integration - Communication service interruptions to community
| Closeout | Technology and Innovation | Difficulty obtaining dedicated and qualified operation and maintenance staff capable of operating the new infrastructure |  |  |  |  | X |  |  | X | [6 empty] | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Recruit operations staff during the construction phase to allow a long period of training, attendance at commissioning and project knowledge
| Design | Technology and Innovation | Technology is new and unfamiliar with owner staff, usure if application is acceptable | X | X | X | X | X | [9 empty] | #N/A | #N/A | #N/A | X |  |  | X | Mitigate | - Conduct pilot testing - Prepare for the possibility of technical failure - conduct multiple design reviews - Ensure project management staff are versed in the technology
| Construction | Technology and Innovation | Use of new construction methods or technologies that result in unexpected technical issues | X | X | X | X | X | [9 empty] | #N/A | #N/A | #N/A |  | X |  |  | Mitigate | - Conduct pilot testing - Prepare for the possibility of technical failure - conduct multiple design reviews - Ensure project management staff are versed in the technology
| All Phases | Ultimate Recipients | Ultimate Recipient, the Owner, does not have qualified staff to manage a project and allows political interference. | X | X | X | X | X | X |  | X | X | X | X | X |  |  | #N/A | #N/A | #N/A | X |  |  |  | Mitigate | - Ensure town elected representatives understand their role and operate within that role once the project has been initiated. - Engage relevant consultant expertise in the areas lacking within the Owner’s organizational framework. - Ensure Owner’s staff are current regarding legislative and occupational health and safety requirements. - Maintain an infrastructure improvement project list that is manageable by the Owner in terms of financial responsibility and operational capacity.
| All Phases | Weather and Natural Disasters | Severe weather event | X | X |  | X | [7 empty] | X |  |  | #N/A | #N/A | #N/A | X | X |  | X | Mitigate | - Ensure design is sufficient for current weather design standards - Include Climate change mitigation strategies - Account for seasonal weather in scheduling Develop disaster preparedness response plan - Protect infrastructure during construction against weather damages
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A
[18 empty] | #N/A | #N/A | #N/A

## Formula (hidden)
Risk Matrix |  | Impact |  |  |  |  | Project Phase | Response Approach | Status | Probability |  | Impact |  | Score | Category
|  | Insignificant | Minor | Moderate | Major | Severe | All Phases | Avoid | Active | 1 - Rare | 1 | 1 - Insignificant | 1 | 1 | Application Quality
|  | 1 | 2 | 3 | 4 | 5 | Initiation | Mitigate | Closed | 2- Unlikely | 2 | 2 - Minor | 2 | 2 | Communication
Probability | Rare | 1 | 2 | 3 | 4 | 5 | Design | Transfer | Mitigated | 3 - Possible | 3 | 3 - Moderate | 3 | 3 | Community and Stakeholder Engagement
| 1 | Low | Low | Low | Medium | Medium | Tender | Acceptance |  | 4 - Likely | 4 | 4 - Major | 4 | 4 | Consultant / Contractor
| Unlikely | 2 | 4 | 6 | 8 | 10 | Construction | Contingency |  | 5 - Almost Certain | 5 | 5 - Severe | 5 | 5 | Cultural Heritage and Social Identity
| 2 | Low | Medium | Medium | High | High | Closeout | [6 empty] | 6 | Environmental
| Possible | 3 | 6 | 9 | 12 | 15 | [7 empty] | 7 | Financial
| 3 | Low | Medium | High | High | Very High | [7 empty] | 8 | Health and Safety
| Likely | 4 | 8 | 12 | 16 | 20 | [7 empty] | 9 | Inadequate Documentation and Reporting
| 4 | Medium | High | High | Very High | Very High | [7 empty] | 10 | Indigenous People and Lands
| Almost Certain | 5 | 10 | 15 | 20 | 25 | [7 empty] | 11 | Land Acquisition
| 5 | Medium | High | Very High | Very High | Very High | [7 empty] | 12 | Legal and Regulatory
[14 empty] | 13 | Political
[14 empty] | 14 | Project Management
[14 empty] | 15 | Quality Assurance / Control
[14 empty] | 16 | Reputation and Public Perception
[14 empty] | 17 | Resource Management
[14 empty] | 18 | Schedule
[14 empty] | 19 | Scope Creep
[14 empty] | 20 | Security
[14 empty] | 21 | Social
[14 empty] | 22 | Supply Chain
[14 empty] | 23 | Technology and Innovation
[14 empty] | 24 | Ultimate Recipients
[14 empty] | 25 | Weather and Natural Disasters